## START UP
EXAMPLE - TO BE COMPLETED
PROJECT MANAGEMENT MENTOR
START-UP CHECKLIST
ADMINISTRATIVE SET-UP
Directories and storages organised
Project Control File & structure in place
Security/ Accesses granted
Project site access
Arrange access to project's site
Install project (war) room
Administrative project tool set-up
Invoicing codes ok
Timesheets open
Contracting
Client
Vendors
Set-up project (recurring) reporting
Identify recurrent reporting needs
Identify reporting requirements
Set-up required tools & templates
PROJECT TEAM
Project team structure designed
Project team structure designed
Needed skills and competencies defined
Staffing request
Names available - Capacity check in organisation
Identified resources with suppliers
GENERAL
Contractual scope reviewed
Statement of work is ok
Clarify scope-resolve issues
Identify the organisation's strategy and link to the project
Detail review of project's/client's site
Initial risk assessment
Define the project strategy/approach
Review organization's methodologies
STAKEHOLDERS
Initial stakeholder group is defined
Prepare draft communication plan
Senior management is briefed
Own company
Client company
Client sponsor is briefed
Say "hi" to "direct" stakeholders
Review questionnaire
Tour the stakeholders
KICKING-OFF EVENT
Plan meeting and invite
Design working procedures
Meet
Project team detail briefed & installed
FIRST SPONSOR MEETING
Why question? - Clarify objective
Which stakeholders should I involve
Priorities on the triple constraint?
Review "values" of triple constraint
OBENG related questions
Check (status) reporting requirements
Desires related to the outcome/result/scope of the project.
Define the members of the Steering Group
PREPARE CLOSING
Identify acceptance criteria
Project acceptance
Product acceptance
Review closing checklist
Incorporate closing activities in project approach

## CLOSE-DOWN
EXAMPLE - TO BE COMPLETED
PROJECT MANAGEMENT MENTOR
CLOSE-DOWN
ADMINISTRATIVE CLOSURE
Close-Out 3rd party contracts
Resolve or transfer open issues
(Conditional) Acceptance
Administrative closing of contract
Transfer responsibilities to operations
Formal responsibility transfer to standing organization
Obtain product acceptance
Start warranty period activities with 3rd parties
Project site
De-install project (war) room
Turn in access badges
Administrative close
Clean-out project contol file
De-install/de-activate project tools
Archive final document/file versions
Destroy non-archived documents and files
Final accounting and invoicing
PROJECT TEAM
Release (human resources)
Thank you to released resources
Evaluations - formal if required
Request feedback on project manager activity
Close-out drink
GENERAL
Project Performance
Last Performance Assessment Done
Project Evaluation Report
Consolidate end-of-phase lessons learned
STAKEHOLDERS
Organize kick-out event/celebration
Closure communication done
Client Satisfaction survey performed
PROJECT SPONSOR
Project Acceptance Signed
Organize final steering group